## Sheet1
CSE325-Software Engineering Project
12BCE0491 & 12BCE0560
Project Plan |  | Requirement Document |  | Design Module |  | Database Design
Start Date: 30-01-15 | S.No: 1 | Start Date: 04-02-15 | S.No: 2 | Start Date: 12-02-15 | S.No: 3 | Start Date: 25-02-15 | S.No: 4
End Date: 03-02-15 | Duration: 5 | End Date: 11-02-15 | Duration: 8 | End Date: 24-02-15 | Duration: 13 | End Date: 04-03-15 | Duration: 7
Test Plan and Test case
[6 empty] | Start Date: 04-03-15 | S.No: 5
[6 empty] | End Date: 10-03-15 | Duration: 6
|  | Bug and Final Report |  | Testing |  | Implementation
|  | Start Date: 20-04-15 | S.No: 8 | Start Date: 12-04-15 | S.No: 7 | Start Date: 11-03-15 | S.No: 6
|  | End Date: 24-04-15 | Duration: 4 | End Date: 20-04-15 | Duration: 8 | End Date: 11-04-15 | Duration: 30